## Slide 1
WAN LINKS MIGRATION
Executive Summary
7 services on 17 physical links across 2 locations (DOZ & DR) and 2 ISPs — every service is flagged for migration.
7
Services in scope
All with end goal “Migrate”
17
Physical links
7 primary · 5 secondary · 5 backup
2
Locations
DOZ 11 links · DR 6 links
2
ISPs
Etisalat 14 links · Du 3 links
Service | ISP | DOZ | DR | Links | Port bandwidth
GPRS | Etisalat | Primary · Secondary | Backup | 3 | 3 × 100 Mbps
Etisalat Payment GW (DSG-Comtrust) | Etisalat | Primary | Backup | 2 | 8 Mbps (DOZ) + 2 Mbps (DR)
Dubai Police | Etisalat | Primary | Backup | 2 | 2 × 8 Mbps
Carrefour | Etisalat | Primary | Secondary | 2 | 2 × 1 Mbps
RTA NOL | Etisalat | Primary · Secondary | — | 2 | 2 × 1 Mbps
CBUAE | Etisalat | Primary · Secondary | Backup | 3 | 3 × 8 Mbps + MGMT 128 Kbps
Du POS links | Du | Primary · Secondary | Backup | 3 | 3 × 512 Kbps
Total | 2 ISPs | 11 links | 6 links | 17 | Aggregate
AMEX, JCB, CUP are live for production services at NEOPAY over Internet VPN, serving transaction authorization from 7th Sep 2026.
Mastercard & VISA connection will stay at Mashreq DC
Notes: Scope: 7 services on 17 physical links — Etisalat 14, Du 3 — across DOZ (11 links) and DR (6 links). Every service carries the end goal "Migrate". Aggregate provisioned port bandwidth is about 355.5 Mbps, of which Etisalat GPRS accounts for 300 Mbps. CBUAE Certax (128 Kbps) rides the same DR link as CBUAE data backup.

## Slide 2
WAN LINKS MIGRATION
POS Traffic Flow & Connectivity | Pilot
Transaction path: POS terminal → ISP GPRS cloud → Mashreq DC → GRE tunnel over ISP dedicated VRF → Postilion at NeoPay DC
Mashreq
Primary Datacenter
DOZ
Mashreq
Secondary Datacenter
KDC
Primary Datacenter
Postilion Server (RT3)
Secondary Datacenter
Postilion Server (RT4)
Inter-DC link · 10G
Inter-DC link · 2G
Etisalat GPRS Cloud
3 × 100 Mbps links to Mashreq
Etisalat
VRF Cloud
4 × GRE tunnels · Mashreq ↔ NeoPay
Du GPRS Cloud
3 × 512 Kbps links to Mashreq
Du
VRF Cloud
4 × GRE tunnels · Mashreq ↔ NeoPay
POS Machine
End-point device
GPRS
Etisalat physical link
Etisalat GRE tunnel
Du physical link
Du GRE tunnel
Inter-DC link
GPRS radio link
Etisalat link on DR is not available now
Expected link delivery 7th Oct
Transaction Latency |  | 
Environment | du | e&
Mashreq Production | Avg. 4 S 42 ms to 5 S 17 ms | Avg. 2 S 51 ms to 3 S 37 ms
Neopay pilot Production | Avg. 4 S 62 ms to 5 S 43 ms | Avg. 2 S 65 ms to 3 S 59 ms
Increased Latency | 20-26 ms | 14-27 ms
Server Live from 7th Sep
Server will be live on 8th Oct
KDC
DXB
Notes: POS terminals reach the Etisalat or Du GPRS cloud over GPRS. Each GPRS cloud is physically connected to both Mashreq datacenters, which are joined by a 10G inter-DC link. Each Mashreq DC has one physical link into each ISP's dedicated VRF cloud, and each NeoPay DC has one physical link from each ISP's VRF cloud. Four GRE tunnels per ISP form a full mesh between the two Mashreq DCs and the two NeoPay DCs, delivering traffic to the Postilion servers. The NeoPay DCs are joined by a 2G inter-DC link.

## Slide 3
WAN LINKS MIGRATION
POS Traffic Flow & Connectivity | Transition State
Transaction path: POS terminal → ISP GPRS cloud → Mashreq DC → GRE tunnel over ISP dedicated VRF → Postilion at NeoPay DC
Mashreq
Primary Datacenter
DOZ
Mashreq
Secondary Datacenter
DR
Primary Datacenter
Secondary Datacenter
Inter-DC link · 10G
Inter-DC link · 2G
Etisalat GPRS Cloud
3 × 100 Mbps links to Mashreq
Etisalat
VRF Cloud
4 × GRE tunnels · Mashreq ↔ NeoPay
Du GPRS Cloud
3 × 512 Kbps links to Mashreq
Du
VRF Cloud
4 × GRE tunnels · Mashreq ↔ NeoPay
POS Machine
End-point device
GPRS
Etisalat physical link
Etisalat GRE tunnel
Du physical link
Du GRE tunnel
Inter-DC link
GPRS radio link
Etisalat link on DR is not available now
Expected link delivery 7th Oct
Transaction Latency |  | 
Environment | du | e&
Mashreq Production | Avg. 4 S 42 ms to 5 S 17 ms | Avg. 2 S 51 ms to 3 S 37 ms
Neopay pilot Production | Avg. 4 S 62 ms to 5 S 43 ms | Avg. 2 S 65 ms to 3 S 59 ms
Increased Latency | 20-26 ms | 14-27 ms
RISK on operating the services via Mashreq for 2 Mondsh
Overall negligible latency 14-27 ms
No of hops increases (4)
Operation dependency with Mashreq
ITSM team alignment which touches the path
Potential ETA increases for resolution for incident
All POS transaction at Neopay
KDC
DXB
Postilion Server (RT3)
Server Live from 7th Sep
Postilion Server (RT4)
Server will be live on 8th Oct
Mashreq – NEOPAY need to agree the risk of operation model for 2 months, till the links are delivered at NEOPAY.
Mastercard & VISA connection will stay at Mashreq DC, the cross-connectivity risk still open for a year
Notes: POS terminals reach the Etisalat or Du GPRS cloud over GPRS. Each GPRS cloud is physically connected to both Mashreq datacenters, which are joined by a 10G inter-DC link. Each Mashreq DC has one physical link into each ISP's dedicated VRF cloud, and each NeoPay DC has one physical link from each ISP's VRF cloud. Four GRE tunnels per ISP form a full mesh between the two Mashreq DCs and the two NeoPay DCs, delivering traffic to the Postilion servers. The NeoPay DCs are joined by a 2G inter-DC link.

## Slide 4
WAN LINKS MIGRATION
POS Traffic Flow & Connectivity | Target State
Transaction path: POS terminal → Etisalat / Du GPRS cloud → Physical link → NeoPay DC router → Centralized firewall → Postilion / TMS
POS Machine
End-point device
60,000 POS machines in the field
Etisalat GPRS Cloud
2 links to KDC · 1 link to DXB
Du GPRS Cloud
2 links to KDC · 1 link to DXB
GPRS
Primary Datacenter
KDC
Router
FW
Firewall
Postilion
TMS
Secondary Datacenter
DXB
Router
FW
Firewall
Postilion
TMS
NeoPay
NeoPay
Inter-DC link · 2G
Migration steps – POS links from Mashreq to NeoPay
# | Migration activity | Target date
1 | Etisalat GPRS link 1 delivery & testing – KDC | TBC
2 | Etisalat GPRS link 2 delivery & testing – KDC | TBC
3 | Etisalat GPRS link delivery & testing – DXB | TBC
4 | Du GPRS link delivery & testing – KDC / DXB | TBC
5 | Router & centralized firewall configuration | TBC
6 | Routing / NAT cutover with ISP – KDC | TBC
7 | Pilot POS migration & transaction validation | TBC
8 | Bulk POS migration in phases (60,000 terminals) | TBC
9 | Decommission GRE tunnels & Mashreq links | TBC
Target state: POS traffic terminates directly at NeoPay – no Mashreq hop, no GRE tunnels. Dates to be confirmed with Etisalat, Du and Mashreq.
Etisalat physical link
Du physical link
Inter-DC link
GPRS radio link